## How to use
Game production kit: budget, schedule, workload and risks for a video game
Free template by José-Manuel Girona Mila, freelance producer · sidestep.publishing@gmail.com
For small studios of 2 to 6 people. One workbook: you enter the team, the rates and the dates once, and every tab follows.
Get started in 15 minutes
1. Settings tab: your team (person, role, day rate, availability) and your milestone dates. Only type in the yellow cells.
2. WBS tab (the list of all the work): one row per task. Type the ID (2.3 = phase 2, task 3: the phase name fills in by itself), the task, the person (from the list), the days to do it once and the number of units. Days and cost are calculated.
3. Look at the Schedule: the bars place themselves between the milestones from Settings, and the cost of each phase comes from the WBS. Nothing to type.
4. Look at the Workload tab, "Load rate" table: who is overloaded, and in which month. Orange from 95%, red above 100%. If it's red, move some work or a date, then go back to step 3.
The rest is optional, for a funding application or a publisher: the "(advanced)" columns, folded under the + buttons above the column letters (ranges, external costs, eligibility, actuals tracking), the Risks tab and the Cash flow tab.
Colors mean the same thing everywhere
Yellow cell: you fill it in. The ones already filled in are the Lumen example: replace them with your own numbers.
Gray cell: calculated, or an explanation. Don't type in it, you would lose the formula.
Light blue header (advanced): optional column, folded at first.
Orange: take a look (a task of more than 10 days in one block, a month loaded at 95% or more, a medium risk).
Red: fix it (overrun, person missing from Settings, past due date, critical risk). Green: all good.
Words used in this workbook
WBS: the list of all the work needed to ship the game, broken down into tasks of 1 to 10 days (work breakdown structure).
Phase: a group of tasks that ends at a milestone. Milestone: a date when something has to be ready (playable prototype, Steam page live, Next Fest, release).
Coordination: time spent coordinating rather than making the game (meetings, tracking, emails, decisions). It's added as a percentage of the work days, 15% by default.
Contingency: a reserve of days and euros for what will go wrong. It stays on its own line and is spent by decision, 10% by default.
Load and capacity: the load is the work days planned for a person in a month; the capacity is the days they really have. Above 100%, they are overloaded.
Forecast (tracking, advanced): where a task will end up if nothing changes, meaning the days already spent plus the days remaining. The variance compares it to the plan.
Excl. VAT: before tax. Every amount in the workbook is excluding VAT. Day rate: the full cost of one work day for that person, payroll taxes included.
What is it for?
To answer the questions you'll be asked before anyone funds the game: how much it costs, when it ships, whether the team can keep up, and what could change all that. The WBS holds the cost, the Schedule the dates, the Workload each person's load, the Risks what could push everything back.
Everything is linked. The Schedule reads each phase's cost from the WBS, the Workload reads each person's days, the Cash flow spreads the Schedule's costs month by month. No more copy and paste: copying from one sheet to another is the top source of errors in Excel.
When: at the end of preproduction to set the budget and the dates, before a grant application or a publisher meeting, then at every milestone to compare plan and actuals.
Who: the producer or the partner who owns the budget, filled in with each person on the team. Everyone checks their own line in the Workload tab.
The example used everywhere: Lumen, a 2D platformer on Steam, 3 people (Léa, Sam, Noé), 12 months, Next Fest in June 2027, release on October 14, 2027. The numbers are for illustration: replace them with yours.
How to use it
Settings. The team: the day rate is a full cost, excluding VAT. Availability: 100% for full time, 80% for four days a week. The Freelance line is for flat fees. Then the key dates, the coordination share (15%), the contingency (10%), the phases, and the public holidays and studio closures.
WBS. Estimate in days. For a task the team has never done, open the advanced columns and fill in Optimistic and Pessimistic: the file uses (optimistic + 4 × likely + pessimistic) ÷ 6, the PERT average. A boss estimated at 6, 9 and 18 days gives 10 days: more than the likely value, because a slip costs more days than a good surprise saves.
WBS, advanced columns. External costs: anything that isn't team time (flat fee work, license, sound library, Steam fees). Eligible: Y if the expense counts toward the grant you're targeting, N if not. Below the table: coordination and contingency, the total per person, the range and the grant cost base.
WBS during production, every month or at every milestone: fill in Spent and Remaining. The forecast (spent + remaining) and the variance are calculated. An empty Remaining is not a zero: until it's filled in, the forecast stays at the plan, or at Spent if that's higher.
Schedule. One row per phase: Start and End are calculated from the dates in Settings (the rule is written in an advanced column). To force a date, type over it. Below the phases, free rows for an event or a task you want to see on the Gantt (demo freeze, buffer before release): they have no cost, the cost stays on the phase row. The Check block must show "-".
Workload. Nothing to enter except absences (vacation, sick leave, training). A person's load is their WBS days, spread over the months of their phase in proportion to working days. Capacity is the month's working days × their availability, minus absences, minus contingency. The last table adds coordination to the team's load.
Risks. One row per risk, written in three parts: cause, event, consequence. "Léa is the only one who knows the code; if she stops, production stops" is something you can act on. "Technical problems" is not. Probability and severity from 1 to 4, using the scale below the matrix. For every orange or red: an action, an owner (one person, never "the team") and a due date. Response, WBS ref. and Impact (advanced columns) give the exposure in days, compared to the WBS contingency.
Cash flow (advanced). Spending per month and running total, from the Schedule, with the chart for your application. Contingency stays on its own line.
To add rows to the WBS or the Risks, insert them in the middle of the table, above the total row: the formulas will pick them up.
Good practice
The 100% rule (PMI, Practice Standard for Work Breakdown Structures): the WBS contains all the work in the project, no more, no less. A funding committee pays for what is written down. Whatever is missing, localization or the Steam page, will get done anyway, but paid for out of the contingency or your evenings.
Tasks of 1 to 10 days. A 30 day row is a row you can't describe yet: break it down, that's where overruns hide. Days per unit turns orange above 10.
Break things down by what the player will see (levels, character, UI), not by discipline. The person is for estimating, the phase is for deciding: you can cut a level, you can't cut "art".
Have the person who will do the work make the estimate, and give a range for anything the team has never done: game feel, bosses, networking, console ports. At the very start of a project, an estimate can be off by a factor of 4 either way (the cone of uncertainty described by McConnell). A range shows that uncertainty and justifies the contingency.
Place the dates that won't move first, then work backward. For a Next Fest on June 14: demo frozen on May 31, Steam page live in mid March to get three months of wishlists before the festival.
Keep coordination and contingency on separate lines. Spread across every task, the contingency gets eaten by the first task that slips, and nobody knows what's left. On its own line, it's spent by decision, and the committee can see it's justified: the Risks exposure, in days, is compared to the WBS contingency.
Don't plan anyone at 100%. Meetings, emails, urgent bugs and playtests take their share. In the example, June overflows for Léa and Noé, the Next Fest month: you see it in November, not the day before.
Estimate the remaining work again at every milestone and freeze a baseline (a dated copy of the file). The cone narrows as the game takes shape: the estimate made after the prototype is better than the one in the application, and that's the one you should steer by.
Handle risks in score order: a red one gets an action dated this week, an orange one an action before the next milestone, a green one is just watched. Start with 8 to 12 risks: a 30 row list for a team of three never gets read again.
Common mistakes
Forgetting everything that isn't content: saving, options, Steam achievements, localization, QA, trailer, Steam page.
Estimating with net salary. An employee's day cost is their gross salary plus employer taxes, divided by the days actually worked (about 215 a year): €36,000 gross gives about €243 a day, not €130. Mixing amounts with and without VAT: if the company gets the VAT back, the VAT paid to a freelancer is not a cost.
Counting unpaid partners' time as an expense. With no salary paid, there's nothing to show, and many funders won't accept it. Put a number on it to know the real cost of the game, but mark it N under Eligible until the funder says yes.
Counting coordination twice: the Coordination line already exists below the WBS, don't add a "project management" task on top of it.
Rewriting the plan when actuals slip. The budget is the frozen baseline: if you touch it up along the way, the variance no longer measures anything. What moves is the remaining work, and so the forecast, which answers the only useful question: where do we end up?
Forgetting public holidays, vacation and closures. In the French example, May 2027 loses 2 weekday holidays (Ascension, Whit Monday), and August drops to 12 working days with a two week closure. Settings removes them from the schedule, the capacity and the cash flow; each person's vacation goes into the Workload absences.
Smoothing a red month over the following months without moving the schedule: the problem slides, it doesn't go away. Making it up with overtime doesn't work either: across hundreds of projects, crunch goes with worse games, not with games that ship on time (Game Outcomes Project).
Writing facts instead of risks. "The budget is tight" is a fact. The risk is what happens because of it: "if the regional grant arrives late, we're €30,000 short for the summer". And rating everything 2 × 2 gives a matrix that sorts nothing: is this risk more of a 1 or more of a 3?
Showing the running total of spending without the contingency. The total budget is the running total plus the contingency, as at the bottom of the Schedule and in the Cash flow.
Excel or Notion
This workbook is for estimating and forecasting, at kickoff and then at every milestone; Notion is for the week to week: current tasks, meeting notes, retrospectives.
Further reading
PMI, Practice Standard for Work Breakdown Structures, 3rd edition (2019). The 100% rule, breakdown levels and work packages.
Steve McConnell, Software Estimation: Demystifying the Black Art (2006). The cone of uncertainty (chapter 4) and how to present an estimate as a range.
Three point estimation (Wikipedia). The formula (a + 4m + b) ÷ 6 used here, and the standard deviation, (pessimistic minus optimistic) ÷ 6.
Construx, The Cone of Uncertainty. At the concept stage, an estimate can be off by a factor of 4; the gap narrows mostly in the first 20 to 30% of the schedule.
CNC (France), Fonds d'aide au jeu vidéo (FAJV). Which preproduction and production costs count, and the 50% cap.
Don Daglow, Producer Bootcamp: Starting Indie Game Production Right (GDC 2019). The five decisions of the first month of production, when the producer has the most influence on whether the game ships.
Blazej Zywiczynski, Fear of Scope: The #1 Reason We Make Ludicrous Production Decisions (GDC 2022). A method for revising scope early, before it decides for you.
Paul Tozour, The Game Outcomes Project, Part 3 (2015). Across hundreds of teams, accurate estimates and a detailed schedule go with games that ship more on time; redesigns along the way go with worse results.
Paul Tozour, The Game Outcomes Project, Part 4: Crunch Makes Games Worse (2015). Overtime doesn't save a late project.
Producer Panel: Managing Your Indie Team (GDC 2015). How indie producers plan with lots of unknowns and avoid burnout on long projects.
Harold Kerzner, Project Management: A Systems Approach to Planning, Scheduling, and Controlling, 13th edition (Wiley, 2022). Network scheduling and resource leveling.
PMI, Risk Management in Portfolios, Programs, and Projects: A Practice Guide (2024, successor to the 2019 standard). The full process: identify, analyze, respond, monitor.
ISO 31000:2018, Risk management, Guidelines. The principles shared by any organization, summarized on the ISO page.
Risk matrix (Wikipedia). How the probability × severity grid is built, and its limits as pointed out by Tony Cox in "What's Wrong with Risk Matrices?" (2008).
Steamworks, Steam Deck compatibility review. The criteria Valve checks (1280 × 800, every action on a controller, text at least 9 pixels), to rate the platform risk.
Want an outside look at your budget, your schedule or your grant application? Write to sidestep.publishing@gmail.com.

## Settings
Settings: the team, the dates, the rules
This tab: the team, the key dates and the shared rules, filled in once. To enter: the yellow cells. Calculated: nothing here, the other tabs read these values.
Yellow: enter | Gray: explanation, don't touch
Team
Person | Role | Day rate (€ excl. VAT) | Availability (%) | Note
Léa | Programming | 350 | 100%
Sam | Art | 300 | 100%
Noé | Design and production | 300 | 80% | Four days a week
Freelance | Contractor on a flat fee |  |  | For flat fees: the amount goes in External costs in the WBS. Not in the workload.
Day rate: a full cost, excluding VAT. Employee (French example): annual gross × about 1.45 (employer taxes) ÷ 215 days worked; €36,000 gross gives about €243 a day, not €130 as with net pay. Freelancer: their day rate excluding VAT. Availability: 100% for full time, 80% for four days a week. Up to 6 people.
Key dates
Milestone | Date | Explanation
Project start | 2026-11-01 | The schedule, the workload and the cash flow cover 12 months starting this month.
Proto | 2027-01-15 | End of the Prototype phase: the core loop can be played and judged.
Steam page | 2027-03-15 | Steam page live. Aim for mid March for a June Next Fest: three months of wishlists before the festival. End of the Steam page phase.
Festival | 2027-04-16 | A show or festival where you present the game. Milestone of the Marketing phase.
Next Fest | 2027-06-14 | June Steam Next Fest, check the date on Steamworks. Milestone of the Next Fest demo phase.
Release | 2027-10-14 | Release on Steam. End of the Polish and release phase.
Rules
Rule | Value | Explanation
Coordination | 15% | Time spent coordinating rather than making the game: meetings, tracking, emails, decisions. Added below the WBS and to the workload. 15% by default; 15 to 20% above 4 people.
Contingency | 10% | A reserve for what will go wrong, on its own line below the WBS, and taken out of the workload capacity. 10% by default; 15% or more for a first game or a new technology.
Polish weeks (advanced) | 11 | The Polish and release phase starts this many weeks before release; production stops the day before.
Demo weeks (advanced) | 3 | The Next Fest demo phase starts this many weeks before Next Fest.
Next Fest length in days (advanced) | 7 | The Next Fest demo phase ends when the festival ends: streams, fixes, replies to players.
Phases
Phase no. | Phase | Schedule color | What the phase contains
1 | Prototype | Game | Core loop, controls, art direction, game design document, grant application
2 | Steam page | Marketing | Capsule, screenshots, short trailer, copy and page launch
3 | Production | Game | The 12 levels, environments, enemies, bosses, menus, sound
4 | Next Fest demo | Game | Demo build, QA, festival week
5 | Polish and release | Game | Debugging, polish, localization, QA, final build
6 | Marketing | Marketing | Social media, devlog, press, festival
7
8
A WBS task ID starts with its phase number (3.2 = phase 3, task 2). Rows 1 to 6 of the Schedule follow this order: if you change the order of the phases, check their dates in the Schedule.
Schedule color: Game (blue) or Marketing (purple).
Public holidays (France, replace with your country's) and studio closures
Date | Name
2026-11-01 | All Saints' Day | One date per row: French public holidays for 2026 and 2027 as the example, plus one week of closure at Christmas and two in August. Days that fall on a weekend change nothing. They are removed from the working days in the schedule, the capacity and the cash flow. Add your own extra days off the same way.
2026-11-11 | Armistice Day
2026-12-25 | Christmas Day
2026-12-28 | Studio closure (Christmas week)
2026-12-29 | Studio closure (Christmas week)
2026-12-30 | Studio closure (Christmas week)
2026-12-31 | Studio closure (Christmas week)
2027-01-01 | New Year's Day
2027-03-29 | Easter Monday
2027-05-01 | Labour Day
2027-05-06 | Ascension Day
2027-05-08 | Victory in Europe Day
2027-05-17 | Whit Monday
2027-07-14 | Bastille Day
2027-08-09 | Studio closure (August)
2027-08-10 | Studio closure (August)
2027-08-11 | Studio closure (August)
2027-08-12 | Studio closure (August)
2027-08-13 | Studio closure (August)
2027-08-15 | Assumption Day
2027-08-16 | Studio closure (August)
2027-08-17 | Studio closure (August)
2027-08-18 | Studio closure (August)
2027-08-19 | Studio closure (August)
2027-08-20 | Studio closure (August)
2027-11-01 | All Saints' Day
2027-11-11 | Armistice Day
2027-12-25 | Christmas Day

## WBS
WBS: what the game costs
This tab: the list of all the work on the game and what it costs. To enter: ID, task, person, days per unit, number of units. Calculated: phase, days, cost.
Days = days per unit × number of units. Cost = days × the person's day rate (Settings) + external costs. Amounts excluding VAT. Advanced columns: + button above the letters.
| Yellow: enter | Gray: calculated, don't touch | Orange: > 10 d | Red: error |  |  |  | Range, costs, eligibility and actuals tracking (advanced)
ID | Phase | Task | Person | Days per unit (d) | Number of units | Days (d) | Cost (€ excl. VAT) | Optimistic (d) (advanced) | Pessimistic (d) (advanced) | Estimate used (d) (advanced) | External costs (€) (advanced) | Grant eligible (Y or N) (advanced) | Spent (d) (advanced) | Remaining (d) (advanced) | Forecast (d) = spent + remaining (advanced) | Variance (d) vs plan (advanced) | Forecast (€ excl. VAT) (advanced) | Comment
1.1 | Prototype | Playable core loop | Léa | 20 | 1 | 20 | 7000 |  |  | 20 |  | Y | 2 | 20 | 22 | 2 | 7700 | Tracking example: 2 d spent, 20 remaining, so 2 more than planned
1.2 | Prototype | Controls and game feel | Léa | 10 | 1 | 11.3 | 3955 | 6 | 22 | 11.3 |  | Y |  |  | 11.3 | 0 | 3955 | Range: the team has never tuned this kind of jump
1.3 | Prototype | Architecture and internal tools | Léa | 5 | 1 | 5 | 1750 |  |  | 5 |  | Y |  |  | 5 | 0 | 1750
1.4 | Prototype | Art exploration and style guide | Sam | 14 | 1 | 14 | 4200 |  |  | 14 |  | Y |  |  | 14 | 0 | 4200 | More than 10 days in one block: break it down (character, environment, UI)
1.5 | Prototype | Main character: sprites and animations | Sam | 18 | 1 | 18 | 5400 |  |  | 18 |  | Y |  |  | 18 | 0 | 5400
1.6 | Prototype | Game design document | Noé | 8 | 1 | 8 | 2400 |  |  | 8 |  | Y |  |  | 8 | 0 | 2400
1.7 | Prototype | Test level and blockout | Noé | 6 | 1 | 6 | 1800 |  |  | 6 |  | Y |  |  | 6 | 0 | 1800
1.8 | Prototype | Prototype playtests | Noé | 2 | 4 | 8 | 2550 |  |  | 2 | 150 | Y |  |  | 8 | 0 | 2550 | One external playtest a week in January (tester expenses)
1.9 | Prototype | Regional grant application | Noé | 5 | 1 | 5 | 1500 |  |  | 5 |  | N |  |  | 5 | 0 | 1500 | Marked N to be safe: writing the application doesn't always count
2.1 | Steam page | Steam capsule and visuals | Freelance |  |  | 0 | 500 |  |  |  | 500 | N |  |  |  |  | 500 | €500 flat fee entered in External costs (advanced column)
2.2 | Steam page | Screenshots and animated GIFs | Sam | 1 | 4 | 4 | 1200 |  |  | 1 |  | N |  |  | 4 | 0 | 1200
2.3 | Steam page | Short trailer (30 s) | Sam | 5 | 1 | 5 | 1500 |  |  | 5 |  | N |  |  | 5 | 0 | 1500
2.4 | Steam page | Copy, tags and page launch | Noé | 3 | 1 | 3 | 900 |  |  | 3 |  | N |  |  | 3 | 0 | 900 | Marked N to be safe: check whether your grant covers marketing
3.1 | Production | Full level: level design and implementation | Noé | 4.5 | 12 | 54 | 16200 |  |  | 4.5 |  | Y |  |  | 54 | 0 | 16200 | 12 levels, 3 per world
3.2 | Production | Environment for one world: tileset and backgrounds | Sam | 14 | 4 | 56 | 16800 |  |  | 14 |  | Y |  |  | 56 | 0 | 16800 | 4 worlds
3.3 | Production | Enemies: behaviors | Léa | 3 | 8 | 24 | 8400 |  |  | 3 |  | Y |  |  | 24 | 0 | 8400 | 8 enemy types
3.4 | Production | Enemies: sprites and animations | Sam | 2.5 | 8 | 20 | 6000 |  |  | 2.5 |  | Y |  |  | 20 | 0 | 6000
3.5 | Production | End of world boss | Léa | 9 | 4 | 40 | 14000 | 6 | 18 | 10 |  | Y |  |  | 40 | 0 | 14000 | Range: the first boss sets the benchmark for the next ones
3.6 | Production | Unique mechanic for each world | Léa | 4 | 4 | 16 | 5600 |  |  | 4 |  | Y |  |  | 16 | 0 | 5600
3.7 | Production | Saving, options, Steam achievements | Léa | 7 | 1 | 7 | 2450 |  |  | 7 |  | Y |  |  | 7 | 0 | 2450
3.8 | Production | Menus and HUD: art | Sam | 5 | 1 | 5 | 1500 |  |  | 5 |  | Y |  |  | 5 | 0 | 1500
3.9 | Production | Menus and HUD: implementation | Léa | 5 | 1 | 5 | 1750 |  |  | 5 |  | Y |  |  | 5 | 0 | 1750
3.10 | Production | Music for one world | Freelance |  | 4 | 0 | 2400 |  |  |  | 2400 | Y |  |  |  |  | 2400 | Freelance composer, about €600 per track
3.11 | Production | Sound effects and audio implementation | Noé | 4 | 1 | 4 | 1450 |  |  | 4 | 250 | Y |  |  | 4 | 0 | 1450 | Licensed sound library
4.1 | Next Fest demo | Demo build and level selection | Léa | 7 | 1 | 7 | 2450 |  |  | 7 |  | Y |  |  | 7 | 0 | 2450 | Demo frozen on May 31, two weeks before the festival
4.2 | Next Fest demo | Fixes during the festival | Léa | 1 | 5 | 5 | 1750 |  |  | 1 |  | Y |  |  | 5 | 0 | 1750
4.3 | Next Fest demo | Demo balancing and tutorial | Noé | 6 | 1 | 6 | 1800 |  |  | 6 |  | Y |  |  | 6 | 0 | 1800
4.4 | Next Fest demo | Streams and festival community work | Noé | 1 | 5 | 5 | 1500 |  |  | 1 |  | N |  |  | 5 | 0 | 1500
4.5 | Next Fest demo | Demo QA on 5 hardware setups | Freelance |  |  | 0 | 750 |  |  |  | 750 | Y |  |  |  |  | 750 | 3 days of freelance QA, Steam Deck included
4.6 | Next Fest demo | Festival banner and visuals | Sam | 3 | 1 | 3 | 900 |  |  | 3 |  | N |  |  | 3 | 0 | 900
5.1 | Polish and release | Debugging and optimization | Léa | 15 | 1 | 16.3 | 5705 | 8 | 30 | 16.3 |  | Y |  |  | 16.3 | 0 | 5705
5.2 | Polish and release | Game feel polish | Léa | 8 | 1 | 8 | 2800 |  |  | 8 |  | Y |  |  | 8 | 0 | 2800
5.3 | Polish and release | Steam Deck port and review | Léa | 4 | 1 | 4 | 1400 |  |  | 4 |  | Y |  |  | 4 | 0 | 1400 | Review requested 4 weeks before release
5.4 | Polish and release | Final build and Steam launch | Léa | 3 | 1 | 3 | 1140 |  |  | 3 | 90 | Y |  |  | 3 | 0 | 1140 | Steam Direct fee: $100 (about €90), recouped once you reach $1,000 in revenue
5.5 | Polish and release | Art polish and effects | Sam | 18 | 1 | 18 | 5400 |  |  | 18 |  | Y |  |  | 18 | 0 | 5400
5.6 | Polish and release | Launch trailer | Sam | 8 | 1 | 8 | 2400 |  |  | 8 |  | N |  |  | 8 | 0 | 2400
5.7 | Polish and release | Localization in 4 languages | Noé | 3 | 1 | 3 | 3300 |  |  | 3 | 2400 | Y |  |  | 3 | 0 | 3300 | Freelance translation, about €600 per language
5.8 | Polish and release | QA testing and bug tracking | Noé | 10 | 1 | 10 | 3000 |  |  | 10 |  | Y |  |  | 10 | 0 | 3000
5.9 | Polish and release | Final balancing | Noé | 5 | 1 | 5 | 1500 |  |  | 5 |  | Y |  |  | 5 | 0 | 1500
6.1 | Marketing | Social media and devlog | Noé | 1 | 12 | 12 | 3600 |  |  | 1 |  | N |  |  | 12 | 0 | 3600 | One day a month
6.2 | Marketing | Press and content creators | Noé | 4 | 1 | 4 | 1200 |  |  | 4 |  | N |  |  | 4 | 0 | 1200
6.3 | Marketing | Press kit | Sam | 2 | 1 | 2 | 600 |  |  | 2 |  | N |  |  | 2 | 0 | 600
|  | Task total |  |  |  | 457.6 | 152400 |  |  |  | 6540 |  | 2 | 20 | 459.6 | 2 | 153100
|  | Coordination, time spent coordinating (15%) |  |  |  | 68.64 | 21879 | [10 empty] | Coordination: days = coordination share × task days; cost = share × cost of team time (external costs not included).
|  | Total before contingency |  |  |  | 526.24 | 174279
|  | Contingency, the reserve (10%) |  |  |  | 52.624 | 17427.9 | [10 empty] | Contingency: a reserve for risks, on its own line. Present it as such to the funder.
|  | Total, coordination 15% and contingency 10% included |  |  |  | 578.864 | 191706.9
Per person
|  | Person | Role |  |  | Days (d) | Cost (€ excl. VAT)
|  | Léa | Programming |  |  | 171.6 | 60150
|  | Sam | Art |  |  | 153 | 45900
|  | Noé | Design and production |  |  | 133 | 42700
|  | Freelance | Contractor on a flat fee |  |  | 0 | 3650
|  | Task total |  |  |  | 457.6 | 152400
Must equal the Task total line. If not, a WBS row has a person who is missing from Settings.
Range: does the contingency cover the pessimistic cases? (advanced)
|  | Tasks, optimistic total (d) |  |  |  | 428
|  | Tasks, total used (d) |  |  |  | 457.6
|  | Tasks, pessimistic total (d) |  |  |  | 514
|  | Contingency (d) |  |  |  | 52.624
|  | Share of the pessimistic gap covered by the contingency |  |  |  | 93.3%
The pessimistic total assumes everything slips at the same time, which rarely happens. Our rule of thumb: a contingency that covers at least half the gap. Below that (red cell), raise the contingency or break down the risky rows. To justify it line by line, see the Risks tab.
For the funding application, amounts excluding VAT (advanced)
|  | Tasks marked eligible (€) |  |  |  |  | 136600
|  | Coordination, if it is salaries (€) |  |  |  |  | 21879
|  | Indicative eligible cost base (€) |  |  |  |  | 158479
|  | Maximum rate of the target grant |  |  |  |  | 50%
|  | Grant cap (€) |  |  |  |  | 79239.5
Example from France: at the CNC video game fund (FAJV), production aid is capped at 50% of production costs, and total public aid can't exceed 50% of the final cost. Check your own funder's rules. Contingency is not an expense: show it on its own line, outside the cost base, unless the funder agrees otherwise.
Days per unit in orange: more than 10 days in one block, break it down if you can. Red variance: overrun; green: savings. "flat fee": a row with no days, costed in external costs.
Forecast = spent + remaining. As long as Remaining is empty, the forecast equals the plan, or Spent if that's higher: a missing entry never looks like a saving.
To add rows, insert them in the middle of the table, above the Task total line: the formulas in the other tabs will pick them up.
Note on G5: Days per unit × number of units. Shows "flat fee" when the task only has external costs.
Note on P5: Forecast: where the task will end up if nothing changes. Spent (days already done) + remaining. As long as Remaining is empty, it equals the plan.

## Schedule
Schedule: what has to be ready before each milestone
This tab: the phases over time, up to release. Nothing you have to enter: Start and End (yellow) come from Settings, type a date to force them. Calculated: cost and bars.
Gantt: one column per week, the number is the Monday's date. Blue bar: game. Purple: marketing. Gray: coordination. ♦: milestone. Pink column: current week.
Yellow: enter | Gray: calculated, don't touch | ♦ milestone | Game | Mktg | Coordination |  |  |  | 2026 | [8 empty] | 2027
[9 empty] | Nov |  |  |  |  | Dec |  |  |  | Jan |  |  |  | Feb |  |  |  | Mar |  |  |  |  | Apr |  |  |  | May |  |  |  |  | Jun |  |  |  | Jul |  |  |  | Aug |  |  |  |  | Sep |  |  |  | Oct |  |  |  | Nov
Phase | Detail | Milestone date | Start | End | Cost (€ excl. VAT) | Working days (d) (advanced) | Color (advanced) | Default date rule (advanced) | time axis 2026-11-02 to 2027-11-01
Prototype | Core loop, controls, art direction, game design document, grant application | 2027-01-15 | 2026-11-01 | 2027-01-15 | 30555 | 48 | Game | From project start to proto | bar: 2027-01-11
Steam page | Capsule, screenshots, short trailer, copy and page launch | 2027-03-15 | 2027-01-18 | 2027-03-15 | 4100 | 41 | Marketing | From the day after proto to the Steam page | bar: 2027-03-15
Production | The 12 levels, environments, enemies, bosses, menus, sound |  | 2027-01-18 | 2027-07-28 | 76550 | 134 | Game | From the day after proto to the day before polish
Next Fest demo | Demo build, QA, festival week | 2027-06-14 | 2027-05-24 | 2027-06-21 | 9150 | 21 | Game | The demo weeks before Next Fest, until the festival ends | bar: 2027-06-14
Polish and release | Debugging, polish, localization, QA, final build | 2027-10-14 | 2027-07-29 | 2027-10-14 | 26645 | 46 | Game | The polish weeks before release (Settings) | bar: 2027-10-11
Marketing | Social media, devlog, press, festival | 2027-04-16 | 2026-11-01 | 2027-10-14 | 5400 | 228 | Marketing | The whole project; milestone: the festival | bar: 2027-04-12
To enter
To enter
Coordination | Meetings, tracking, decisions: spread over the whole project |  | 2026-11-01 | 2027-10-14 | 21879 | 228 | Coordination | The whole project
Optional detail: an event or a task you want to see on the Gantt. No cost here: it stays on the phase row.
Production | Vertical slice: one complete playable world | 2027-03-26 |  |  |  |  | Game | bar: 2027-03-22
Steam page | Capsule delivered by the freelancer | 2027-02-26 |  |  |  |  | Marketing | bar: 2027-02-22
Next Fest demo | Demo freeze, two weeks before the festival | 2027-05-31 |  |  |  |  | Game | bar: 2027-05-31
Polish and release | Steam Deck review requested, 4 weeks before release | 2027-09-16 |  |  |  |  | Game | bar: 2027-09-13
Polish and release | Buffer: free time before release |  | 2027-09-30 | 2027-10-13 |  | 10 | Game
Check and budget (€ excl. VAT)
| Cost placed in the schedule (phases and coordination) |  |  |  | 174279
| WBS total before contingency |  |  |  | 174279
| Gap to explain |  |  |  | 0 | Must show "-". If not, a WBS task has an ID whose phase doesn't exist in Settings.
| Contingency (reserve, not in the schedule) |  |  |  | 17427.9
| Total budget |  |  |  | 191706.9
Orange cost: the phase has a cost in the WBS but no dates here, so it is neither in the workload nor in the cash flow.

## Workload
Workload: who is overloaded, and in which month
This tab: who has too much on their plate, and in which month. To enter: absences (yellow). Calculated: everything else, from the WBS, the Schedule and Settings. Folded details: + button on the left.
Yellow: enter | Gray: calculated | 95 to 100% | > 100%
Month |  |  | 2026-11-01 | 2026-12-01 | 2027-01-01 | 2027-02-01 | 2027-03-01 | 2027-04-01 | 2027-05-01 | 2027-06-01 | 2027-07-01 | 2027-08-01 | 2027-09-01 | 2027-10-01 | Total
Working days in the month (holidays and closures removed) |  |  | 20 | 18 | 20 | 20 | 22 | 22 | 19 | 22 | 21 | 12 | 22 | 21 | 239
1. Planned load (days): each person's WBS days, spread over the months of their phase. Detail: + button on the left
Person | Role | Availability | 2026-11-01 | 2026-12-01 | 2027-01-01 | 2027-02-01 | 2027-03-01 | 2027-04-01 | 2027-05-01 | 2027-06-01 | 2027-07-01 | 2027-08-01 | 2027-09-01 | 2027-10-01 | Total | In the WBS
Léa | Programming | 100% | 15.125 | 13.6125 | 14.4282 | 13.7313 | 15.1045 | 15.1045 | 16.4733 | 23.6759 | 14.4056 | 8.1652 | 14.9696 | 6.8043 | 171.6 | 171.6
Sam | Art | 100% | 13.5088 | 12.1579 | 15.082 | 16.6552 | 15.9061 | 13.4915 | 12.5089 | 15.6343 | 12.7997 | 6.8879 | 12.6278 | 5.7399 | 153 | 153
Noé | Design and production | 80% | 12.6535 | 11.3882 | 12.0886 | 11.5236 | 11.8711 | 11.0662 | 12.7001 | 18.9234 | 10.4802 | 5.5378 | 10.1526 | 4.6148 | 133 | 133
Team total |  |  | 41.2873 | 37.1586 | 41.5987 | 41.9102 | 42.8817 | 39.6622 | 41.6823 | 58.2336 | 37.6855 | 20.5908 | 37.7499 | 17.159 | 457.6 | 457.6
Orange total: some of the person's days fall outside the 12 months, or on a phase with no dates in the Schedule.
2. Absences (working days: vacation, sick leave, training)
Person | Role | Availability | 2026-11-01 | 2026-12-01 | 2027-01-01 | 2027-02-01 | 2027-03-01 | 2027-04-01 | 2027-05-01 | 2027-06-01 | 2027-07-01 | 2027-08-01 | 2027-09-01 | 2027-10-01 | Total
Léa | Programming | 100% | [10 empty] | 3 |  | 3
Sam | Art | 100% | [8 empty] | 3 |  |  |  | 3
Noé | Design and production | 80% | [5 empty] | 2 | [6 empty] | 2
3. Capacity (days): working days × availability, minus absences, minus contingency. Detail: + button on the left
Person | Role | Availability | 2026-11-01 | 2026-12-01 | 2027-01-01 | 2027-02-01 | 2027-03-01 | 2027-04-01 | 2027-05-01 | 2027-06-01 | 2027-07-01 | 2027-08-01 | 2027-09-01 | 2027-10-01 | Total
Léa | Programming | 100% | 18 | 16.2 | 18 | 18 | 19.8 | 19.8 | 17.1 | 19.8 | 18.9 | 10.8 | 17.1 | 18.9 | 212.4
Sam | Art | 100% | 18 | 16.2 | 18 | 18 | 19.8 | 19.8 | 17.1 | 19.8 | 16.2 | 10.8 | 19.8 | 18.9 | 212.4
Noé | Design and production | 80% | 14.4 | 12.96 | 14.4 | 14.4 | 15.84 | 14.04 | 13.68 | 15.84 | 15.12 | 8.64 | 15.84 | 15.12 | 170.28
Team total |  |  | 50.4 | 45.36 | 50.4 | 50.4 | 55.44 | 53.64 | 47.88 | 55.44 | 50.22 | 30.24 | 52.74 | 52.92 | 595.08
4. Load rate (%) = load ÷ capacity. Orange from 95%, red above 100%
Person | Role | Availability | 2026-11-01 | 2026-12-01 | 2027-01-01 | 2027-02-01 | 2027-03-01 | 2027-04-01 | 2027-05-01 | 2027-06-01 | 2027-07-01 | 2027-08-01 | 2027-09-01 | 2027-10-01 | Total
Léa | Programming | 100% | 84.03% | 84.03% | 80.16% | 76.29% | 76.29% | 76.29% | 96.34% | 119.6% | 76.22% | 75.6% | 87.54% | 36% | 80.79%
Sam | Art | 100% | 75.05% | 75.05% | 83.79% | 92.53% | 80.33% | 68.14% | 73.15% | 78.96% | 79.01% | 63.78% | 63.78% | 30.37% | 72.03%
Noé | Design and production | 80% | 87.87% | 87.87% | 83.95% | 80.03% | 74.94% | 78.82% | 92.84% | 119.5% | 69.31% | 64.09% | 64.09% | 30.52% | 78.11%
Contingency is already taken out of capacity: so orange starts at 95%, not 85%. You fix a red month by moving a bar in the Schedule, by cutting, or by adding a person.
5. Team, coordination included (days)
|  |  | 2026-11-01 | 2026-12-01 | 2027-01-01 | 2027-02-01 | 2027-03-01 | 2027-04-01 | 2027-05-01 | 2027-06-01 | 2027-07-01 | 2027-08-01 | 2027-09-01 | 2027-10-01 | Total
Planned load of the people |  |  | 41.2873 | 37.1586 | 41.5987 | 41.9102 | 42.8817 | 39.6622 | 41.6823 | 58.2336 | 37.6855 | 20.5908 | 37.7499 | 17.159 | 457.6
Coordination (15%) |  |  | 6.1931 | 5.5738 | 6.2398 | 6.2865 | 6.4323 | 5.9493 | 6.2523 | 8.735 | 5.6528 | 3.0886 | 5.6625 | 2.5739 | 68.64
Total load |  |  | 47.4804 | 42.7323 | 47.8386 | 48.1968 | 49.314 | 45.6115 | 47.9346 | 66.9687 | 43.3384 | 23.6795 | 43.4124 | 19.7329 | 526.24
Plannable capacity, contingency removed |  |  | 50.4 | 45.36 | 50.4 | 50.4 | 55.44 | 53.64 | 47.88 | 55.44 | 50.22 | 30.24 | 52.74 | 52.92 | 595.08
Team load rate |  |  | 94.21% | 94.21% | 94.92% | 95.63% | 88.95% | 85.03% | 100.1% | 120.8% | 86.3% | 78.31% | 82.31% | 37.29% | 88.43%
Days still free |  |  | 2.9196 | 2.6277 | 2.5614 | 2.2032 | 6.126 | 8.0285 | -0.054648 | -11.5287 | 6.8816 | 6.5605 | 9.3276 | 33.1871 | 68.84
Coordination (meetings, tracking, decisions) is not in the people's rows: it's added here to the whole team's load.
Calculation: share of each phase in each month, in proportion to working days. Detail: + button on the left
Phase (Schedule) | Start | End | 2026-11-01 | 2026-12-01 | 2027-01-01 | 2027-02-01 | 2027-03-01 | 2027-04-01 | 2027-05-01 | 2027-06-01 | 2027-07-01 | 2027-08-01 | 2027-09-01 | 2027-10-01 | Total
Prototype | 2026-11-01 | 2027-01-15 | 41.67% | 37.5% | 20.83% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 100%
Steam page | 2027-01-18 | 2027-03-15 | 0% | 0% | 24.39% | 48.78% | 26.83% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 100%
Production | 2027-01-18 | 2027-07-28 | 0% | 0% | 7.463% | 14.93% | 16.42% | 16.42% | 14.18% | 16.42% | 14.18% | 0% | 0% | 0% | 100%
Next Fest demo | 2027-05-24 | 2027-06-21 | 0% | 0% | 0% | 0% | 0% | 0% | 28.57% | 71.43% | 0% | 0% | 0% | 0% | 100%
Polish and release | 2027-07-29 | 2027-10-14 | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 4.348% | 26.09% | 47.83% | 21.74% | 100%
Marketing | 2026-11-01 | 2027-10-14 | 8.772% | 7.895% | 8.772% | 8.772% | 9.649% | 9.649% | 8.333% | 9.649% | 9.211% | 5.263% | 9.649% | 4.386% | 100%
|  |  | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
|  |  | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
Total under 100%: the phase runs past the 12 months of the plan. Example: a phase of 20 working days with 5 in June puts 25% of its days in June.

## Risks
Risks: what could derail the game, and who is on it
This tab: what could derail the game, and who is on it. To enter: one row per risk (yellow). Calculated: score and level. 1 to 4 scale on the right, below the matrix.
| Yellow: enter | Calculated | 1 to 3 | 4 to 6 | 8 to 16 | Score = probability × severity: green low, orange watch, red critical. | [10 empty] | Matrix: open risks per cell
ID | Risk: cause, event, consequence | Probability (1 to 4) | Severity (1 to 4) | Score (P × S) | Level | Action | Owner | Due date | Status | Category (advanced) | Response (advanced) | Review date (advanced) | WBS ref. (advanced) | Impact if it happens (d) (advanced) | Exposure (d) (advanced) | Sort (advanced) | Probability ↓ Severity → | 1 | 2 | 3 | 4
R01 | The demo gets built in June, the month when Léa and Noé are already above 100% in the workload. If it isn't frozen in time, it crashes for players during Next Fest and the reviews stay on the page. | 3 | 4 | 12 | Critical | Demo freeze on May 31; 3 days of freelance QA on 5 setups including Steam Deck; move 6 days of production from June to July. | Noé | 2027-05-31 | Open | Schedule | Reduce | 2026-11-02 | 4 | 10 | 6.5 | 12.0066 | 4 | 0 | 0 | 0 | 0
R02 | The capsule freelancer delivers after the end of February. The Steam page opens after March 15 and reaches Next Fest with fewer wishlists. | 2 | 3 | 6 | Watch | Brief sent before January 15, sketch approved mid February, delivery on February 26; a second freelancer lined up as backup. | Sam | 2027-02-26 | Open | Contractor | Reduce | 2026-11-02 | 2.1 | 5 | 1.8 | 6.0019 | 3 | 1 | 1 | 1 | 1
R03 | The regional grant is approved but paid late. We're about €30,000 short to pay for the summer. | 3 | 3 | 9 | Critical | Plan B costed before applying: a 3 world version, partner contributions, an interest free personal loan; keep two months of spending in the bank. | Noé | 2027-03-15 | Open | Funding | Reduce | 2026-11-02 | 1.9 | 15 | 9.8 | 9.0099 | 2 | 0 | 1 | 1 | 1
R04 | Léa is the only one who knows the code. If she stops for several weeks, production stops and the release slips by as much. | 2 | 4 | 8 | Critical | Code on Git with peer review every Friday; architecture written up in 2 pages; a freelance programmer identified and briefed as backup. | Noé | 2027-01-29 | In progress | Team | Reduce | 2026-11-02 | 3 | 30 | 10.5 | 8.0106 | 1 | 0 | 0 | 0 | 0
R05 | Every playtest adds a mechanic. Level design goes from 4.5 to 6.5 days per level and production spills into polish. | 3 | 2 | 6 | Watch | Mechanics list frozen at the end of the prototype; a new idea replaces one or goes on the "after release" list. Noé decides. | Noé | 2027-01-15 | Open | Scope | Avoid | 2026-11-02 | 3.1 | 24 | 15.6 | 6.0157 | Number = open risks in the cell. Color = P × S score zone. Read from top right (severe and likely) to bottom left.
R06 | UI designed for the mouse and text too small. The Steam Deck review gives "Playable" instead of "Verified" and the game loses that badge on the store. | 2 | 2 | 4 | Watch | Test on Steam Deck from the prototype on; every action on a controller; no text under 12 pixels at 1280 × 800; review requested 4 weeks before release. | Léa | 2027-09-16 | Open | Platform | Reduce | 2026-11-02 | 5.3 | 4 | 1.4 | 4.0015
R07 | Translators get a spreadsheet with no screenshots and no length limits. Text gets cut off in the UI and mistranslations show up in reviews. | 3 | 1 | 3 | Low | One screenshot and one character limit per string; an in game review by a native speaker for each language, about 1 day each. | Noé | 2027-09-15 | Open | Quality | Reduce | 2026-11-02 | 5.7 | 3 | 2 | 3.0021
R08 | The prototype runs poorly on a low end laptop. Testing happens on powerful machines and the problem comes back in the middle of polish. | 1 | 3 | 3 | Low | Profiling on a 2019 laptop with every weekly build. Done: the prototype holds 60 frames per second. | Léa | 2026-11-02 | Closed | Tech | Reduce | 2026-11-02 | 1.1 | 8 |  |  | Summary
[17 empty] | Open risks | 7
[17 empty] | Critical (8 to 16) | 3
[17 empty] | Watch (4 to 6) | 3
[17 empty] | Low (1 to 3) | 1
Does the WBS contingency cover the risks?
[17 empty] | Total exposure of open risks (d) | 47.6
[17 empty] | WBS contingency (d) | 52.624
[17 empty] | Coverage (contingency ÷ exposure) | 110.6%
[17 empty] | Reading | The contingency covers the calculated exposure
Coverage doesn't need to be exact: under 100%, the contingency won't hold if the risks play out as expected.
The 5 highest open scores: agenda for the weekly meeting
[17 empty] | Rank | ID | Score | Owner | Due date | Risk
[17 empty] | 1 | R01 | 12 | Noé | 2027-05-31 | The demo gets built in June, the month when Léa and Noé are already above 100% in the workload. If it isn't frozen in time, it crashes for players during Next Fest and the reviews stay on the page.
[17 empty] | 2 | R03 | 9 | Noé | 2027-03-15 | The regional grant is approved but paid late. We're about €30,000 short to pay for the summer.
[17 empty] | 3 | R04 | 8 | Noé | 2027-01-29 | Léa is the only one who knows the code. If she stops for several weeks, production stops and the release slips by as much.
[17 empty] | 4 | R05 | 6 | Noé | 2027-01-15 | Every playtest adds a mechanic. Level design goes from 4.5 to 6.5 days per level and production spills into polish.
[17 empty] | 5 | R02 | 6 | Sam | 2027-02-26 | The capsule freelancer delivers after the end of February. The Steam page opens after March 15 and reaches Next Fest with fewer wishlists.
Scale
[17 empty] | Probability | Rating
[17 empty] | < 20%: unlikely over the life of the project | 1
| Open risks |  |  | 7 | [12 empty] | 20 to 50%: possible, about one chance in three | 2
| of which critical (score 8 and up) |  |  | 3 | [12 empty] | 50 to 80%: likely if we do nothing | 3
| Total exposure of open risks (d) |  |  | 47.6 | [12 empty] | > 80%: almost certain, it's already happening | 4
| Exposure = average probability of the band (1: 10%, 2: 35%, 3: 65%, 4: 90%) × impact in days. The rough number of days this risk will cost on average, to compare with the WBS contingency. | [15 empty] | Severity | Rating
| Due date in red: overdue on a risk that isn't closed. Review date in orange: more than 30 days without a review. | [15 empty] | Nuisance: a few days, absorbed without touching the dates or the budget | 1
| A closed risk stays on the list: it shows the next funder what you managed to anticipate. The matrix and the exposure no longer count it. | [15 empty] | One phase hit: one to two weeks late, or a feature cut down | 2
[17 empty] | Key date missed (Next Fest, application deadline) or more than 10% of the budget | 3
[17 empty] | Failure: the game doesn't ship, the funding falls through, the studio closes | 4
Rate severity against the project's goals (date, budget, quality), not against discomfort.
Note on C4: 1: under 20%. 2: 20 to 50%. 3: 50 to 80%. 4: over 80%, it's already happening.
Note on D4: 1: a few days, absorbed. 2: one phase hit, 1 to 2 weeks. 3: key date missed or more than 10% of the budget. 4: the game doesn't ship.

## Cash flow
Cash flow: when the money goes out (advanced)
This tab (advanced): spending month by month, for a funding application or a publisher. Nothing to enter: everything comes from the Schedule. Amounts excluding VAT.
The cost of each Schedule row is spread over its working days, holidays and closures removed, to the day. Amounts excluding VAT.
Month | 2026-11-01 | 2026-12-01 | 2027-01-01 | 2027-02-01 | 2027-03-01 | 2027-04-01 | 2027-05-01 | 2027-06-01 | 2027-07-01 | 2027-08-01 | 2027-09-01 | 2027-10-01 | Total
Spending in the month (€ excl. VAT) | 15124.1447 | 13611.7303 | 15471.2063 | 15818.2679 | 16300.0947 | 15200.0947 | 15741.6402 | 21735.8089 | 14525.1222 | 8386.6064 | 15375.4451 | 6988.8387 | 174279
Running total (€ excl. VAT) | 15124.1447 | 28735.875 | 44207.0813 | 60025.3492 | 76325.4438 | 91525.5385 | 107267.1787 | 129002.9876 | 143528.1098 | 151914.7162 | 167290.1613 | 174279
Contingency (€ excl. VAT, reserve, Total column) | [12 empty] | 17427.9
Total budget with contingency (€ excl. VAT) | [12 empty] | 191706.9
Share of the budget spent by month end (%) | 7.889% | 14.99% | 23.06% | 31.31% | 39.81% | 47.74% | 55.95% | 67.29% | 74.87% | 79.24% | 87.26% | 90.91%
Contingency stays on its own line: it's a reserve, not a planned expense. In the last column, what's left is the unspent contingency.
Check
Cost placed in the Schedule (phases and coordination) | 174279
Spending spread over the 12 months | 174279
Outside the 12 months or without dates | 0 | Must show "-". If not, a Schedule row has a cost but no dates, or runs past the 12 months.
Detail per Schedule row (€ excl. VAT)
Schedule row | 2026-11-01 | 2026-12-01 | 2027-01-01 | 2027-02-01 | 2027-03-01 | 2027-04-01 | 2027-05-01 | 2027-06-01 | 2027-07-01 | 2027-08-01 | 2027-09-01 | 2027-10-01 | Total
Prototype | 12731.25 | 11458.125 | 6365.625 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 30555
Steam page | 0 | 0 | 1000 | 2000 | 1100 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4100
Production | 0 | 0 | 5712.6866 | 11425.3731 | 12567.9104 | 12567.9104 | 10854.1045 | 12567.9104 | 10854.1045 | 0 | 0 | 0 | 76550
Next Fest demo | 0 | 0 | 0 | 0 | 0 | 0 | 2614.2857 | 6535.7143 | 0 | 0 | 0 | 0 | 9150
Polish and release | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1158.4783 | 6950.8696 | 12743.2609 | 5792.3913 | 26645
Marketing | 473.6842 | 426.3158 | 473.6842 | 473.6842 | 521.0526 | 521.0526 | 450 | 521.0526 | 497.3684 | 284.2105 | 521.0526 | 236.8421 | 5400
| 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Coordination | 1919.2105 | 1727.2895 | 1919.2105 | 1919.2105 | 2111.1316 | 2111.1316 | 1823.25 | 2111.1316 | 2015.1711 | 1151.5263 | 2111.1316 | 959.6053 | 21879
Total | 15124.1447 | 13611.7303 | 15471.2063 | 15818.2679 | 16300.0947 | 15200.0947 | 15741.6402 | 21735.8089 | 14525.1222 | 8386.6064 | 15375.4451 | 6988.8387 | 174279
Expense or payment: here the expense lands in the month the work is done. A freelancer paid at 30 days pushes the cash out by one month: shift it in your final cash flow plan, next to the money coming in (grant, publisher advance, contributions).